## Progress Log
AML Watchlist Pipeline — Progress Log
Scoreme / Resurgent India ¦ Updated as work progresses
Date | Sources Completed | Total Records | Agencies | Key Highlights
7 May 2026 | 51 | 27,386 | 25+ | Pipeline built from scratch. Three-tier fetch architecture (static + browser + Playwright). OCR engine for scanned PDFs. FCRA cracked via Playwright form-driving (14,830 records). Bank of India OCR (2,502), IOB wilful defaulters (2,605), BHEL debarred firms (15), UGC fake universities (32). 19 custom scrapers. All data in PostgreSQL with change detection.
7 May 2026 | 55 | 27,901 | 28+ | MOD debarred firms via OCR (82 records). Coal India banning orders (11). RVNL disqualified contractors via OCR (379 records). Jharkhand Police rewarded naxals — custom Hindi scraper (43 records). ESIC confirmed login-only portal. Total: 4 new sources, 515 new records.
11 May 2026 | 90 | 146653 | 69+ | Sources: 71 -> 90 (+19 in one day). Records: 105,840 -> 146,653. Key adds: FIU x3 lists (13,377 — NBFC High-Risk + Non-Compliant NBFC + Compliance Orders/Judgements), NSDL Accounts Frozen on SEBI Direction (25,615 from in-page table), UNSC Consolidated Sanctions (1,009 — 737 individuals + 272 entities), CCI Antitrust Orders (1,200 via direct JSON API), BIS Enforcement Activities (914 via POST endpoint, 3 types x 5 FYs), Delhi Police Wanted + Proclaimed (148 combined), BSE Defaulter/Expelled Members (105 via Angular JS-bundle parse), Income Tax Defaulters (96 via Liferay Headless API), AMFI Suspended ARN (89), ED Proclamation Notices (8 via Umbraco API), NHB CoR-cancelled HFCs (50), Kerala Police Wanted (1). Tooling: scripts/screen.py CLI screening; scripts/validate_production.py daily DQ gate (5 checks, 0 CRITICAL); run_all.sh + activate_cron.sh for daily automation; utils/smart_change_detector.py for data-aware diffs; scripts/entity_resolution.py producing 7,035 cross-agency clusters. Data quality: 40,000+ SEBI names extracted from order titles (post-pass and now in-scraper), BOI OCR rebuilt with column-aware parsing, NSE/ICEX/Meghalaya tail cleanup.
Add new rows above this line as work progresses. Each row = one update with date, metrics, and what was done.

## Current Snapshot
AML Watchlist Pipeline — Current Snapshot
Last Updated: 11 May 2026
Pipeline Overview |  | Coverage Breakdown
Total Sources Tracked | 251 | In Progress (Partial Data) | 32
Sources Fully Scraped | 90 | Pending URL Discovery | 83
Total Records in Database | 146653 | Requires JS Engine | 20
Distinct Agencies with Data | 69+ | Requires Credentials/Login | 8
Top 15 Agencies by Record Count
# | Agency | Watchlist | Records
1 | SEBI | All lists (combined) | 44479
2 | National Securities Depository Limited (NSDL) | All lists (combined) | 29492
3 | NSE | All lists (combined) | 26451
4 | MHA | All lists (combined) | 14926
5 | Financial Intelligence Unit (FIU) | All lists (combined) | 13401
6 | BSE | All lists (combined) | 7188
7 | IOB | All lists (combined) | 2605
8 | Competition Commission of India (CCI) | All lists (combined) | 1200
9 | UNSC | All lists (combined) | 1009
10 | Bureau of Indian Standards (BIS) | All lists (combined) | 914
11 | CBI | All lists (combined) | 801
12 | Oil and Natural Gas Corporation (ONGC) | All lists (combined) | 487
13 | RVNL | All lists (combined) | 368
14 | Bank of India (BOI) | All lists (combined) | 361
15 | National Spot Exchange Limited (NSEL) | All lists (combined) | 333
Update the numbers in this sheet whenever the Progress Log gets a new entry.

## Technical Architecture
Technical Architecture
Fetch Layer | Tier 1: Static HTTP (Scrapling Fetcher) — 80% of sources Tier 2: Browser Render (StealthyFetcher + headless Chromium) — auto-upgrade when JS detected Tier 3: Playwright Form-Driving — for ASP.NET forms, interactive pages
PDF Engine | Strategy 1: pdfplumber table extraction Strategy 2: pdfplumber text extraction Strategy 3: Tesseract OCR at 200 DPI (50 page cap)
Database | PostgreSQL 16 — watchlist_records table, 17-column schema Master CSV export on every run
Change Detection | Content hashing per source, layout change alerts Cron-ready for daily automation (run_all.sh)
Quality System | Automated audit: nav-menu garbage detection, duplicate detection, empty data detection Honest status tiers: completed / partial / failed / url_not_found / js / restricted
Custom Scrapers | 19 source-specific scrapers for agencies with unique page structures Generic engine handles ~80% of sources automatically
Future: Knowledge Graph | Entity resolution across agencies → risk scoring → screening API Phase 4, after scraping coverage is stable
Intelligence Layer (added 11 May 2026) | Smart change detection: utils/smart_change_detector.py — hashes extracted CSV rows (canonical payload), persists added/removed/modified events to PG watchlist_changes; HIGH-PRIORITY flags for CBI/NIA/MHA/UNSC additions, removals, and >10% drops. Entity resolution: scripts/entity_resolution.py — 4-strategy matcher (exact, token, subset, trigram) with prefix blocking; produced 7,035 cross-agency clusters in 17 min over 119k records; risk scoring by agency severity (CBI/NIA/MHA/UNSC=30, SEBI/BSE/NSE/FIU=20, banks=15, others=10, capped at 100). Production validator: scripts/validate_production.py — 5-check daily gate (schema, name-quality, record-count vs expected_min, duplicates, freshness); exit non-zero on CRITICAL; wired into run_all.sh between combine and load_to_db.